## Attendees
Name | Role | Org | Email | Required | Notes

## Day 1 Agenda
Time | Activity | Facilitator | Output | Status
09:00 | Recap of questionnaire |  | Shared baseline | Not started
09:30 | Customer presents current-state topology |  | Captured diagram | Not started
10:30 | Whiteboard: hubs / spokes / ER / VPN / DNS / edge |  | Annotated diagram | Not started
12:00 | Lunch
13:00 | Gap identification vs CAF network topology |  | Gap list | Not started
14:00 | Day 1 readout |  | Top 5 risks + opportunities | Not started

## Day 2 Agenda
Time | Activity | Facilitator | Output | Status
09:00 | Reference architecture menu walkthrough |  | Shortlist | Not started
10:00 | Hub-spoke vs Virtual WAN decision |  | Decision recorded | Not started
11:30 | Firewall Premium vs 3rd-party NVA |  | Decision recorded | Not started
13:00 | Front Door vs App Gateway vs both |  | Decision recorded | Not started
14:00 | Seed decision log (≥ 10 decisions) |  | Filled decision log | Not started

## Day 3 Agenda
Time | Activity | Facilitator | Output | Status
09:00 | Backlog generation |  | Epic-level workstreams | Not started
10:00 | T-shirt sizing |  | Sized backlog | Not started
11:00 | Sequencing: quick wins, foundational, transformational |  | Sequenced backlog | Not started
13:00 | Roadmap on a page |  | Roadmap diagram | Not started
14:30 | Workshop close |  | Signed-off roadmap, owners, next steps | Not started

## Decision log
# | Decision | Options considered | Decision taken | Owner | Date
1 | Topology base | Hub-spoke / VWAN Std / Secured VHub
2 | Hybrid connectivity | ER Std / ER Prem / ER Direct / VPN / dual
3 | Edge ingress | AFD / AppGW / AFD + AppGW
4 | Firewall tier | Az FW Std / Az FW Prem / NVA
5 | DDoS tier | Network / IP / none
6 | DNS authority | Azure DNS / Private Resolver / on-prem AD-DNS
7 | Bastion model | Per-region Std / central + ER
8 | Observability core | NSG Flow + Insights / Connection Monitor / 3rd-party
9 | Segmentation primitive | NSG+ASG / Firewall policy / NVA
10 | IaC tool | Bicep / Terraform / ARM / ALZ Accelerator

## Risks + assumptions
# | Type | Description | Impact | Mitigation | Owner | Due | Status

## Traffic flows
# | Flow name | Source | Destination | Path narrative | Components | Latency budget | Owner
1 | User to public app
2 | SQL query to PaaS storage
3 | Admin RDP to spoke VM